## EDI
ID | Task Name | Duration (Hours)
1 | Project Kick-off | 11
1.1 | Project Kick-off | 1
1.2 | Weekly Status Meetings | 9
1.3 | Project Close-out and Handover | 1
2 | Integration Development | 100
2.1 | Customer Integration (MineralTree and Caliber, Dual Sync, near real time) | 30
2.1.1 | Requirements Gathering | 6
2.1.2 | Query MineralTree and Caliber API | 6
2.1.3 | Create mappings between MineralTree and Caliber | 8
2.1.4 | Build the Integration process flow | 8
2.1.5 | Error Handling | 2
2.2 | GL Account Integration (MineralTree and Caliber, Dual Sync, near real time) | 32
2.2.1 | Requirements Gathering | 6
2.2.2 | Query MineralTree and Caliber API | 6
2.2.3 | Create mappings between MineralTree and Caliber | 8
2.2.4 | Build the Integration process flow | 10
2.2.5 | Error Handling | 2
2.3 | Invoice Integration (MineralTree and Caliber, Dual Sync, near real time) | 38
2.3.1 | Requirements Gathering | 6
2.3.2 | Query MineralTree and Caliber API | 10
2.3.2 | Create mappings between MineralTree and Caliber | 10
2.3.4 | Build the Integration process flow | 10
2.3.5 | Error Handling | 2
4 | Documentation | 22
4.1 | Documentation for project functionality for all items listed in section 3 | 20
4.2 | Recording of Integration Demonstration | 2
5 | Testing | 48
5.1 | System Test | 24
5.2 | UAT | 24
6 | Production Implementation | 6
6.1 | Test connectivity in production environment | 2
6.2 | Implement to production | 2
6.3 | Post go live support | 2
| Project Total | 187